Education and Learning Directorate

School/ELC Annual School Improvement Planning

# 2025-2026

School: North West Community Campus Nursery

# Date:  May 2025

SCHOOL IMPROVEMENT PLAN 2025 – 2026  (Limit the number of priorities to ensure they are manageable and achievable.)

| School Priority /Improvement Area for Learners |  | To develop a shared vison, values and aims relevant to the ELC setting |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Evidence to support decision to prioritise this area (include baseline measures) |  | ### Outcomes for Learners/School Community |  | Key Tasks |  |
| Current vision, values and aims need reviewed) and updated (last updated 2022) to reflect current practice. Stakeholders unfamiliar with Vision, Values and Aims. |  | All stakeholders will be involved in reviewing and updating our vision, values and aims informed by the needs of our setting. The VVA are shaped by the needs of our community and is informed by current thinking in early learning pedagogy. Children and families are supported to understand the vision, aims and values of the ELC in the most appropriate way. |  | - Involve parent/carers in working parties using Learning Journals, coffee mornings, questionnaires to gather and include ideas and opinions. - Involve children in choosing words that reflect the nursery vision, values and aims. - Update Nursery handbook to include the new vision, values and aims. - Whole staff working party to gather and include ideas and opinions. - VVA regularly shared with children daily and weekly through everyday life and celebration of learning. - All staff will regularly share VVA with parents – through learning journals, social media, daily communication. |  |
| NIF Priority |  | NIF Driver |  | HGIOS?4 / HGIOELC QIs/National Standard Criteria |  |
| - Improvement in children and young people’s health and wellbeing |  | ELC Improvement Parental Engagement ELC Leadership Practitioner Professionalism |  | HGIOELC 1.3: Leadership of change ELC QI: Leadership and Management of Staff & Resources |  |
| Responsible/Lead Person | Time Allocations |  | Funding – including PEF |  | Expected Completion Date |
| Nursery Manager | Through Collegiate time |  | Nursery DSM |  | February 2026 |
| Parental and Learner Engagement Opportunities |  |  | Linkage to Framework for Inclusion |  |  |
| Parent/Carer Working Parties Pupil voice Sharing of VVA |  |  | Policy and Procedure |  |  |

| School Priority /Improvement Area for Learners |  | Providing an environment and experiences that supports children’s wellbeing and involvement facilitating creativity, thinking and independence. |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Evidence to support decision to prioritise this area (include baseline measures) |  | ### Outcomes for Learners/School Community |  | Key Tasks |  |
| For identified learners, engagement in experiences is fleeting. Leuven Scale to be used as a baseline to determine impact. Observing Nursery environment, there are opportunities to further enhance experiences that spark children's curiosity and engagement. Staff would benefit from additional ideas and resources to support with this. |  | Staff use their knowledge of how children learn when making observations of children and as a basis for future planning. Children will experience high-quality learning experiences. Improvement in staff knowledge and skills to provide engaging spaces and experiences Children will have a high level of involvement throughout the session. Through exploratory play, all children have the opportunity to develop and apply investigative, problem solving and thinking skills. Approaches to learning and teaching enable children to become immersed in activities that interest them and to play for extended periods. Practitioners take care not to rush children. The learning environment, including the provision of open-ended and natural resources and the adaptability of space, encourage creativity. The structure and flexibility of the day also nurture creativity. ELC setting will have well managed and available resources Children’s wellbeing and developmental needs are met through appropriately planned spaces and experiences. Children use a wide variety of technology meaningfully to develop and extend their learning |  | - Leuven Scale of Involvement as a baseline and to measure impact throughout. - ECERS & ITERS (Early/Infant Childhood Environment Rating Scale) in Term 2 & 4 - Maintaining and organising resources - Purchasing appropriate resources including technology - Room layout to be adapted - Staff to visit other settings - Elkland Environmental Scales to be used - Invitations to play. Create a resource bank of ideas - Training for staff – Elkland/Planning in the Moment/ - Staff to use Early Years’ ‘Environments - Learning Potential Through Play’ Checklists - Care Inspectorate Creativity document |  |
| NIF Priority |  | NIF Driver |  | HGIOS?4 / HGIOELC QIs/National Standard Criteria |  |
| Improvement in children and young people’s health and wellbeing - Improvement in achievement, particularly in literacy and numeracy. |  | ELC Improvement Curriculum and Assessment ELC Leadership Practitioner Professionalism |  | HGIOELC:2.3 Learning, Teaching & Assessment HGIOELC:3.3 Developing creativity and skills for life and learning ELC QI: Children Experience High Quality Spaces ELC QI: Learning, Teaching & Assessment ELC QI: Play & Learning |  |
| Responsible/Lead Person | Time Allocations |  | Funding – including PEF |  | Expected Completion Date |
| Nursery Manager Equity and Excellence Lead | Through collegiate hours Daily Practise |  | DSM Budget |  | May 2025 |
| Parental and Learner Engagement Opportunities |  |  | Linkage to Framework for Inclusion |  |  |
| Learner engagement in experiences |  |  | Inclusive Community Wellbeing |  |  |

| School Priority /Improvement Area for Learners |  | To improve our approach to becoming a rights respecting setting |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Evidence to support decision to prioritise this area (include baseline measures) |  | ### Outcomes for Learners/School Community |  | Key Tasks |  |
| Our setting has currently achieved Unicef Silver Rights Award for rights Respecting Schools. We are working towards the Gold Rights Award. |  | Within and beyond our setting there is a shared understanding of wellbeing and children’s rights. Full account is taken of children’s rights and is considered in respect of their stage of development including when planning learning across the curriculum. All Children will experience a rights based approach which will have a positive impact on their health and wellbeing. |  | Practitioners knowledge and understanding to be supported through CPL in relation to a further 8 children’s rights. - Article 12 - Article 13 - Article 14 - Article 16 - Article 19 - Article 23 - Article 27 - Article 29 Nursery UNCRC Charter to be created in consultation with children and families. The settings policies and procedures to be reviewed to ensure they promote the rights of children and that this is embedded in all that we do. Rights based approach to be used by all nursery leaders and practitioners through interactions. |  |
| NIF Priority |  | NIF Driver |  | HGIOS?4 / HGIOELC QIs/National Standard Criteria |  |
| Improvement in children and young people's health and wellbeing Placing the human rights and needs of every child and young person at the centre of education; |  | ELC Improvement Parental Engagement Practitioner Professionalism |  | HGIOELC 3.1: Ensuring Wellbeing, Equity and inclusion ELC QI: Nurturing Care and Support ELC QI: Wellbeing, Inclusion & Equality |  |
| Responsible/Lead Person | Time Allocations |  | Funding – including PEF |  | Expected Completion Date |
| Nursery Manager Equity and Excellence Lead | Through collegiate time Daily practise |  | Nursery DSM |  | May 2025 |
| Parental and Learner Engagement Opportunities |  |  | Linkage to Framework for Inclusion |  |  |
| Parent/Carer Working Parties Pupil voice |  |  | Relationships and Rights Wellbeing Policy and Procedure Inclusive Community |  |  |